# STATEMENT OF WORK

##### Description of Work

Concrete sidewalk with a 200 ft. (l) x 3 ft. (w) x 6 inch (d) curving concrete sidewalk as part of an overall landscaping project.

Work includes:

- Prepare subgrade for new sidewalk.

- Construct forms for new 3600 cubic foot concrete sidewalk (200’ long x 3’ wide x 6” thick).

- Pour and level concrete.

- Water cure concrete.

- Remove forms.

Contractor will remove from the premises all debris, trash, excess materials, forms, stakes, empty sacks, etc., caused by the work. The site will be left with a neat appearance.

##### Location of Work

123 West Main Street,

Seattle, WA

##### Schedule

- Construct forms: 9/23

- Prepare subgrade: 9/24

- Pour and level concrete: 9/25

- Water cure concrete: 9/26 – 9/29

##### Applicable Standards & Specifications

- Concrete must be M15 grade or better.

- Maximum .50 water-to-cement ratio.

- 2 inches of crushed rock used as subgrade.

- Contractor must adhere to all applicable city and county ordinances and building codes.

- Forms should either be metal or wood, free of warp, and of a depth equal to the depth of the concrete.

##### Acceptance and Payment Criteria

- Forms must be constructed in accordance with landscape architect plans (included in the procurement package).

- Concrete must be completely water cured before forms are removed.

- Once leveled, the concrete should be free of honeycombs.

- All exposed corners are to be edged or rounded to the radius shown on the plans.

- Contractor will remove from the premises all debris, trash, excess materials, forms, stakes, empty sacks, etc., caused by the work. The site will be left with a neat appearance.