Original networks

| All activities | A | B | C | D | E | F | G | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration | 13 | 6 | 6 | 6 | 10 | 20 | 5 | *** |
| Original critical path | 13 | 6 | 6 |  |  | 20 | 5 | 50 |
| Alternative path 1 | 13 |  |  |  | 10 | 20 | 5 | 48 |
| Alternative path 2 | 13 | 6 | 6 | 6 |  |  | 5 | 36 |

After crashing G   2 weeks

| All activities | A | B | C | D | E | F | G | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration | 13 | 6 | 6 | 6 | 10 | 20 | 3 | *** |
| Original critical path | 13 | 6 | 6 |  |  | 20 | 3 | 48 |
| Alternative path 1 | 13 |  |  |  | 10 | 20 | 3 | 46 |
| Alternative path 2 | 13 | 6 | 6 | 6 |  |  | 3 | 34 |

After crashing B   2 weeks

| All activities | A | B | C | D | E | F | G | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration | 13 | 4 | 6 | 6 | 10 | 20 | 3 | *** |
| Original critical path | 13 | 4 | 6 |  |  | 20 | 3 | 46 |
| Alternative path 1 – add’l critical path | 13 |  |  |  | 10 | 20 | 3 | 46 |
| Alternative path 2 | 13 | 4 | 6 | 6 |  |  | 3 | 32 |

After crashing F   7 weeks

| All activities | A | B | C | D | E | F | G | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration | 13 | 4 | 6 | 6 | 10 | 13 | 3 | *** |
| Original critical path | 13 | 4 | 6 |  |  | 13 | 3 | 39 |
| Alternative path 1 - add’l critical path | 13 |  |  |  | 10 | 13 | 3 | 39 |
| Alternative path 2 | 13 | 4 | 6 | 6 |  |  | 3 | 32 |

After crashing C   1 week

| All activities | A | B | C | D | E | F | G | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration | 13 | 4 | 5 | 6 | 10 | 13 | 3 | *** |
| Original critical path | 13 | 4 | 5 |  |  | 13 | 3 | 38 |
| Alternative path 1 – New critical path | 13 |  |  |  | 10 | 13 | 3 | 39 |
| Alternative path 2 | 13 | 4 | 5 | 6 |  |  | 3 | 31 |

After crashing A   3 weeks

| All activities | A | B | C | D | E | F | G | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration | 10 | 4 | 5 | 6 | 10 | 13 | 3 | *** |
| Original critical path | 10 | 4 | 5 |  |  | 13 | 3 | 35 |
| Alternative path 1 – New critical path | 10 |  |  |  | 10 | 13 | 3 | 36 |
| Alternative path 2 | 10 | 4 | 5 | 6 |  |  | 3 | 28 |