| Activity | Description | Expense Estimates |
| --- | --- | --- |
| 1.1.4.2.1 Conduct Planning Meetings | - Four 2-hour planning meetings are scheduled, each with 15 key team members in attendance. - Two of the meetings will be catered lunch meetings. | - Internal labor: 120 hours. - Catered lunches: $15.00 per person. |
| 1.1.4.2.2 Arrange Location | - Research to locate a suitable facility. Rent necessary equipment. | - Internal labor: 20 hours. - Facility rent: 5,000 sq. ft. at $0.40 to $0.50 each. - Equipment rent: 600 chairs at $0.25 to $0.40 each. - Equipment rent: 3 Large Monitors at $200.00 each per hour for two hours. |
| 1.1.4.2.3 Arrange Staffing | - Coordinate all staff and travel for the public meeting. | - Internal labor: 50 hours. - Travel: 1 panel member from Florida at approximately $1,000.00. - Moderator: Standard fee of $500.00 for the 2-hour event. - Security: 6 guards for 4 hours at $50.00 per hour. |
| 1.1.4.2.4 Publicize Event | - Design, print, and mail 10,000 postcards. - Newspaper advertising. | - Internal labor: 60 hours. - Postcards: Printing and postal charges at $0.20 to $0.25 each. - Advertising: $1000.00 flat fee. |
| 1.1.4.2.5 Hold Event | - Requirements as needed to set up for, hold, and clean up after the event. | - Internal labor: 35 hours. - Additional: 2 speakers at $50.00 each per hour for 2 hours. |