| Activity | Expense Estimates | Calculations | Cost of Activity |
| --- | --- | --- | --- |
| 1.1.4.2.1 Conduct Planning Meetings | - Internal labor: 120 hours. - Catered lunches: $15.00 per person. | 15 people * 80 per hr rate * 4 days * 2 hours = $9,600 Lunch = 15 rate * 15 people * 2days = $450 | $10,050 |
| 1.1.4.2.2 Arrange Location | - Internal labor: 20 hours. - Facility rent: 5,000 sq. ft. at $0.40 to $0.50 each. - Equipment rent: 600 chairs at $0.25 to $0.40 each. - Equipment rent: 3 Large Monitors at $200.00 each per hour for two hours. | 20 hrs * 80 per hr rate = $1,600 5,000 sq ft * 0.40 rate = $2,000 5,000 sq ft * 0.50 rate = $2,500 600 chairs * 0.25 rate = $150 600 chairs * 0.40 rate = $240 3 monitors * 200 rate * 2 hours = $1,200 | $4,950 to $5,540 |
| 1.1.4.2.3 Arrange Staffing | - Internal labor: 50 hours. - Travel: 1 panel member from Florida at approximately $1,000.00. - Moderator: Standard fee of $500.00 for the 2-hour event. - Security: 6 security guards for 4 hours at $50.00 per hour. | 50 hrs * 80 per hr rate = $4,000 1,000 travel rate = $1,000 500 moderate rate = $500 6 guards * 4 hrs * 50 rate = $1,200 | $6,700 |
| 1.1.4.2.4 Publicize Event | - Internal labor: 60 hours. - Postcards: Printing and postal charges at $0.20 to $0.25 each. - Advertising: $1,000.00 flat fee. | 60 hrs * 80 per hr rate = $4,800 10,000 postcards * 0.20 rate = $2,000 10,000 postcards * 0.25 rate = $2,500 1,000 advertising rate = $1,000 | $7,800 to $8,300 |
| 1.1.4.2.5 Hold Event | - Internal labor: 35 hours. - Additional: 2 speakers at $50.00 each per hour for 2 hours. | 35 hrs * 80 per hr rate = $2,800 2 speakers * 50 rate * 2 hrs = $200 | $3,000 |

Total Cost Estimate for the Public Meeting Work Package: 	$32,500 to $33,590