GCCG e-Banking Portal

Risk Management Plan

| Prepared by: | <Student name> |
| --- | --- |
| Date (MM/DD/YYYY): | <Today’s date> |

- Methodology

The major processes followed in risk management are risk identification, risk prioritization, risk response planning, and risk control.

The e-Banking Portal project is a non-complex project and is not required to follow the quantitative risk analysis process.

- The format and scales for the risk register

| Risk No. | Category | Risk Event (Uncertainty) | Probability of Occurrence (0.1-0.3-0.5-0.7-0.9) | Detectability | Symptom | Urgency (H- =<7 M- 7-21 D L-21 +) | Impact on Time (0.05-0.10-0.20-0.40-0.80) | Risk Exposure - time | Response |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Column | Description |
| --- | --- |
| Risk No. | The risk numbering will be R-nnn e.g., R001, R002, etc. |
| Category | Category to include: Technology, Data, Usability, Contractual obligations, Implicit requirements/expectations, Vendors and partners, Process, People |
| Probability of Occurrence | Probability [P] Scale used will be 0.1, 0.3, 0.5, 0.7, and 0.9 |
| Detectability | Detectability [D] is rated as Easy to detect 0.1 and Difficult to detect 0.7 |
| Urgency | Urgency [U] If necessary to be focused in the following ranges: - =< 7 days implies High Urgency (Number 0.9) - Between 8 to 21 days implies Medium Urgency (Number 0.4) - More than 21 days implies Low Urgency (Number 0.1) |
| Impact on Time | Impact [I] on the objective timely completion of the project will be in the range scale of 0.05, 0.10, 0.20, 0.40 & 0.80 to be used for the values respectively for the values 1, 2, 4, 6, 8 days expected schedule overrun. |
| Risk Exposure - Time | [P] * [I] * [D] * [U] |

Probability and Impact Matrix

4.	Roles and Responsibilities

4.1	Organization Risk Manager

- Assumes general oversight of risk management in the organization.

4.2	Program Sponsor

- Ensures that risk registers are updated annually.

- Reviews and approves the risk registers prepared by program managers.

- Accepts responsibility for risk identification and accountability for those that have not been adequately identified or assessed.

4.3	Project/Program Managers

- Prepare, review, and update a risk register in their area of responsibility.

- Continuously review risks and controls of their operations with a view to ensuring risks are effectively mitigated.

5.	Frequency of Updating Risk Registers

- Risk registers should be tracked once every two weeks.