## Sheet1
WBS: TRN001.0 | Title: Systems Engineering
Assigned to: Student Description: The Systems Engineering work package will deal with planning for work-processes and tools to handle the GCCG E-banking Portal project.
WBS # | Activity
TRN001 | Systems Engineering
TRN001.1 | Technical Planning
TRN001.1.1 | Create technical plan
TRN001.1.2 | Estimate resources
TRN001.1.3 | Plan reviews
TRN001.1.4 | Plan authorization
TRN001.2 | Technical Supervision
TRN001.2.1 | Analyze technical requirements
TRN001.2.2 | Document supervision plan
TRN001.2.3 | Review supervision plan
TRN001.2.4 | Obtain authorization
TRN001.3 | Business Requirements Definition
TRN001.3.1 | Gather requirements
TRN001.3.2 | Document business requirements
TRN001.3.3 | Review requirements
TRN001.3.4 | Obtain authorization